## Shopenzer Testcases
|  |  |  | Date | 2022-11-18
|  |  |  | Team ID | PNT2022TMID08862
|  |  |  | Project Name | Car Resale value Prediction
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Comments | TC for Automation(Y/N) | BUG ID | Executed By
HomePage_tst_cse1 | Functional | Home Page | Verify all the UI elements in Home page rendered properly | Html,css | 1.Enter URL and click go 2.Verify all the UI elements displayed or not | cleaned_dataset.csv | All the UI elements rendered properly | Working as expected | Pass |  | Y |  | vasanthabalan m, dhineshraj,muthu,naveen,kavin
HomePage_tst_cse2 | Functional | Home Page | Verifiy the Data Entry page can be reachable. | Hhtml,css | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button. | cleaned_dataset.csv | User should navigate to Data Entry Page | Working as expected | Pass |  | Y |  | vasanthabalan m, dhineshraj,muthu,naveen,kavin
DataEntryPage_tst_cse1 | Functional | Data Entry Page | Verify all the UI elements in Data Entry page rendered properly | Html,css | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button in the home page 4. Verify all the UI elements displayed or not | cleaned_dataset.csv | All the UI elements rendered properly | Working as expected | Pass |  | Y |  | vasanthabalan m, dhineshraj,muthu,naveen,kavin
DataEntryPage_tst_cse2 | Functional | Data Entry Page | Verify user is able to enter all values | Html,css,Csv files | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button in the home page 4. Verify all the UI elements displayed or not 5. Verify if all values can be entered | Maruti Suzuki Swift','Maruti',2019,100,'Petrol' | User should be able to enter all values in data entry page | Working as expected | Pass |  | Y |  | vasanthabalan m, dhineshraj,muthu,naveen,kavin
DataEntryPage_tst_cse3 | Functional | Data Entry Page | Verifiy the Output Display page can be reachable. | Html,css,Csv files | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button in the home page 4. Verify all the UI elements displayed or not 5. Verify if all values can be entered 6. Press the submit Button | - | User should navigate to Output Display Page | Working as expected | Pass |  | Y |  | vasanthabalan m, dhineshraj,muthu,naveen,kavin
OutputDisplayPage_tst_cse1 | Functional | Output Display Page | Verify all the UI elements in Output Display page rendered properly | Html,css,Csv files,implemet python using Flask,api key using ibm cloud | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button in the home page 4. Verify all the UI elements displayed or not 5. Verify if all values can be entered 6. Press the submit Button 7. Verify all the UI elements displayed or not | cleaned_dataset.csv,pickle file | All the UI elements rendered properly | Working as expected | Pass |  | Y |  | vasanthabalan m, dhineshraj,muthu,naveen,kavin
OutputDisplayPage_tst_cse2 | Functional | Output Display Page | Verify user is able to get predicted result | Html,css,Csv files,implemet python using Flask,api key using ibm cloud | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button in the home page 4. Verify all the UI elements displayed or not 5. Verify if all values can be entered 6. Press the submit Button 7. Verify all the UI elements displayed or not 8. Verify if the predicted value is displayed or not | cleaned_datsets.csv,api keys | Predited Car Resale Value is displayed on the page | Working as expected | Pass |  | Y |  | vasanthabalan m, dhineshraj,muthu,naveen,kavin

## Testscearnios
Test Scenarios
1 | Verify user is able to see home page?
2 | Verify user is able to navigate to data entry page?
3 | Verify user is able to see data entry page?
4 | Verify user is able to enter values in the fields?
5 | Verify user is able to navigate to output display page?
6 | Verify user is able to view the output display page?
7 | Veriify user is able to view the car resale value output in the output display page?